## Cover Doc PATP
PT. Indosat Tbk
PO No: 4810042172
Physical Acceptance Test Procedure
Location | : | [SITE_ID] | [SITE_NAME]
Device Type | : | [DEVICE_TYPE]
NE Hostname | : | [HOSTNAME]
SOW | : | [SCOPE_OF_WORK]
Prepared by
PT. Sisindokom Lintasbuana
Maret 2024

## Approval Log
Physical Acceptance Test Procedure
Acceptance Test Approval Page
Approval Status | Date | Signature
PT. Indosat Tbk
Name : Apep Solihin
Position : Acceptance MSH
Status : Approved
PT. Sisindokom Lintasbuana | 2025-12-19
Name : Dian Effriansyah
Position : Acceptance Team
Status : Approved
Comments :

## BOQ
Physical Acceptance Test Procedure
Bill of Quantity
NO | PO Number | Line Item | PO Type | Material Number | Material Description |  | Actual | 3rd party Material
1 | 4810011787 | 50 | HW | 1100026391 | N540-24Q8L2DD-SYS |  | 1 | No
2 | 4810011787 | 130 | HW | 1100026459 | SFP-10G-ER-S |  | 3 | No
3 | 4810011787 | 180 | HW | 1100014374 | GLC-LH-SMD |  | 14 | No
4 | 4810011787 | 200 | HW | 1100014376 | GLC-TE |  | 1 | No
Date : PT. Sisindokom Lintas Buana Representative, | [5 empty] | Date : IOH Representative,
( Wendy Fajar Munandar ) | [5 empty] | ( Apep Solihin )

## 1. Checklist Item
Physical Acceptance Test Procedure
ATP Checklist
No | Items | Expected Result | Check Result
1. Prerequiresite check list
1.1 | Labelling (including Device, Optical Patch cord, AC PDB’s MCB and Rectifier’s MCB. | All label are complete as per MDR | 🗹 | OK | ☐ | NOK | ☐ | NA
1.2 | Ensure the connected patchcord on OTB port is according to port allocation during integration | Port is connected as per design
2. Power Supply Test
2.1 | Ground/Eart measurement between chassis and power plug | 0 | ☐ | OK | ☐ | NOK | 🗹 | NA
2.2 | DC supply voltage | -38.4 V to -57.6 V | 🗹 | OK | ☐ | NOK | ☐ | NA
2.3 | LED status on Power module | GREEN | 🗹 | OK | ☐ | NOK | ☐ | NA
3. Check of Other Hardware LEDs Status
3.1 | Fan | GREEN | 🗹 | OK | ☐ | NOK | ☐ | NA
3.2 | Status | NORMAL | 🗹 | OK | ☐ | NOK | ☐ | NA
3.3 | Alarm Critical | GREEN | 🗹 | OK | ☐ | NOK | ☐ | NA
3.4 | Alarm Major | GREEN | 🗹 | OK | ☐ | NOK | ☐ | NA
4. Fail Over Test of Power Entry Module (PEM)
4.1 | Did second PEM able to take over the load when the other PEM was removed? | Backup system is working | 🗹 | OK | ☐ | NOK | ☐ | NA
4.2 | Did the system rebooted by itself when one of the PEM was removed? | System is rebooted | 🗹 | OK | ☐ | NOK | ☐ | NA
5. Environmental Test
5.1 | The device can detect the fan and fan speed. | Can detect the fan | 🗹 | OK | ☐ | NOK | ☐ | NA
5.2 | The device current temperature. | can show device temperature | 🗹 | OK | ☐ | NOK | ☐ | NA
6. Accecories Material
6.1 | Was the ESD Wrist Strap Installed at the router? | ESD wrist is avalable | ☐ | OK | ☐ | NOK | 🗹 | NA
6.2 | Was the Console Cable Installed at the router? | Console cable is avaialable | ☐ | OK | ☐ | NOK | 🗹 | NA
7. Rectifier Source
7.1 | Router connected to the 2 different rectifier? Only for Core site | Has 2 power source | 🗹 | OK | ☐ | NOK | ☐ | NA
7.2 | Space avaialable at sorrounding cabinet | space avaialable | 🗹 | OK | ☐ | NOK | ☐ | NA

## 2. Log Capture
Physical Acceptance Test Procedure
ATP Log Capture
Please attach log file in txt format containt of below item
insert log file HERE
8. Basic System Configuration for Management
Log Capture of Setting up of router for management access, configuration files, and software images.
9. PORT Setup and Test
Purpose
Pre-provision ports and interfaces after the line card and MDA types are specified.
Note: Must be test for all port (1/10 Gb).
Equipment
> Optical Fiber Patch cord
> Optical attenuator
> S/XFP Modules
10. Reboot and Retain Configuration
Purpose
Configuration changes are made or modified configuration is saved in compact flash. Upon reboot, previous configuration remains intact.
Catpre log result after system is rebooted
11. Environmental Log
Purpose
The device can detect the fan and fan speed, and show device temperature

## 3. Router Photo
Physical Acceptance Test Procedure
Appendix 2. Router Photograph
Front View, Rear View, Front Space, Rear Space (ESD and Console Cable must can be seen if any)
[PHOTO_FRONT_VIEW] | [PHOTO_REAR_VIEW] | [PHOTO_FRONT_SPACE]
Power Cable to Rectifier and MCB Power Connection Main and Stand By), and DC Power supply measurement
Physical Acceptance Test Procedure
Appendix 2. Router Photograph
Grounding Cable
Connection Router to ODP/OTB

## 4. Router Photo_1
Physical Acceptance Test Procedure
Appendix 2. Router Photograph
Router environment
For insert module process, please include photograph before and after

## Netgear Capture
Physical Acceptance Test Procedure
Appendix 2. Router Photograph
Task Netgear MOS : TSK-MOS-20251104003215,TSK-MOS-20251104003219
Task Netgear Dism : TSK-MVC-20251104002165

## PL Clearance
NO | Punchlist Item | Severity Level | Rectification Date | Status | Vendor PIC | ISAT PIC | Remarks
| Approved by, |  |  |  |  | Approved by,
_______________
| PT. INDOSAT Tbk |  |  |  |  | PT. Sisindokom Lintasbuana

## PL Form
PUNCHLIST PHOTOS
Checklist Item No.
BEFORE | AFTER
Comment | Comment
Checklist Item No.
BEFORE | AFTER
Comment | Comment
Checklist Item No.
BEFORE | AFTER
Comment | Comment
Checklist Item No.
BEFORE | AFTER
Comment | Comment
Checklist Item No.
BEFORE | AFTER
Comment | Comment
Checklist Item No.
BEFORE | AFTER
Comment | Comment

## Guidance
Physical Acceptance Test Procedure
1. Introduction
This test plan forms the acceptance document for Router on Indosat project. This test plan includes testing of basic functionalities and operation of the standalone installed Router, as well as the link connectivity and other advanced function such as routing, MPLS signaling and Pseudowire. The tests are conducted to ensure proper boot up, functioning of the hardware of router and prepare the router for system integration.
Tests conducted will be in the form of:
| Checklist | Guidance
1 | Collection of harware and software information | all hardware SN and part number must be tagging via Netgear, and all hardware and software info should be found in log file information
2 | Measurement using tester equipment | DC power measured with tester tools
3 | Power up status
4 | Visual Test through LEDs | all LED indicators must normal (green)
5 | Ensure that all installed cards or modules can be detected by the system
6 | System console commands to check on router status
7 | Switch reboot and recover of previously configured parameters | Configuration changes are made or modified configuration is saved in compact flash. Upon reboot, previous configuration remains intact. Configuration is the same after reboot

## Table Content - Delete- (hidden)
Physical Acceptance Test Procedure
Table of Contents
Table of Contents |  |  | i
Acceptance Test Approval Page |  |  | iii
Bill of Quantity |  |  | 4
ATP Prerequisites Checklist |  |  | 5
1. Introduction |  |  | 6
2. Identify hardware ………. Router |  |  | 7
| Purpose |  | 7
3. Power Supply Test |  |  | 8
| Purpose |  | 8
| Procedure (For DC Power Supply) : |  | 8
| Expected Result |  | 8
4. Check of Other Hardware LEDs Status |  |  | 9
| Purpose |  | 9
| Procedure |  | 9
| Expected Result |  | 9
5. Basic System Configuration for Management |  |  | 10
| Purpose |  | 10
| Procedure |  | 10
| Expected Result |  | 10
6. PORT Setup and Test |  |  | 11
| Purpose |  | 11
| Procedure |  | 11
| Expected Result |  | 11
7. Reboot and Retain Configuration |  |  | 12
| Purpose |  | 12
| Procedure |  | 12
| Expected Result |  | 12
8. Fail Over Test of Power Entry Module (PEM) |  |  | 13
| Purpose |  | 13
| Procedure |  | 13
| Expected Result |  | 13
9. Enviroment Test |  |  | 14
| Purpose |  | 14
| Procedure |  | 14
| Expected Result |  | 14
10. Enviromental Information |  |  | 15
| Purpose |  | 15
| Procedure |  | 15
| Expected Result |  | 15
11. Activity Log |  |  | 16
| Purpose |  | 16
| Procedure |  | 16
| Expected Result |  | 16
12. Photo Documentation |  |  | 17
| Purpose |  | 17
| Procedure |  | 17
| Expected Result |  | 17
13. Rectifier Source |  |  | 18
| Purpose |  | 18
| Procedure (For DC Power Supply) |  | 18
| Expected Result |  | 18
14. Space Available |  |  | 19
| Purpose |  | 19
| Procedure |  | 19
| Expected Result |  | 19
| Actual Measurement Result |  | 19